## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | kumkum | 2026-07-10 | FastAPI backend endpoint /analyze throws a 422 Unprocessable Entity due to malformed payload schema from Streamlit. | Sprint 1 | kumkum | Logical | Updated the Pydantic data models in schemas.py to match the exact JSON body structure sent by the frontend client. | 2026-07-11 | Closed | Payload validation error resolved; frontend and backend now communicate data structures seamlessly.
2 | kumkum | 2026-07-11 | Streamlit application hangs indefinitely when Google Gemini API encounters a rate-limiting quota error. | Sprint 1 | kumkum | Logical | Implemented Python try-except blocks around the LLM API call with exponential backoff and user-friendly error notifications. | 2026-07-12 | closed | App now catches rate limit exceptions smoothly and displays an alert banner on the UI dashboard.
3 | kumkum | 2026-07-12 | Code parser utility (detector.py) fails to correctly tokenize multi-line strings and raw docstrings in Python files. | Sprint 1 | kumkum | Standards | Refactored the AST parsing logic in detector.py to properly handle edge cases in raw file tokenization. | 2026-07-13 | Closed | Source code files are successfully parsed into clean structural nodes without syntax warnings.
4 | kumkum | 2026-07-13 | Multi-agent coordinator fails to pass context sequentially between the Security Agent and the Remediation Agent. | Sprint 1 | kumkum | Logical | Restructured the agent orchestration pipeline loop in backend services to pass state dictionaries explicitly across steps. | 2026-07-14 | closed | Agents now execute sequentially, handing off vulnerability insights to the code patch generator successfully.
5 | kumkum | 2026-07-14 | ChromaDB vector embedding lookup returns irrelevant code snippets during RAG retrieval queries. | Sprint 1 | kumkum | Maintainability | Tuned the chunk size and overlapping parameters during text splitting and updated the similarity search threshold configuration. | 2026-07-15 | Closed | Vector database now accurately fetches relevant OWASP secure coding guidelines matching the scanned code.
6 | kumkum | 2026-07-15 | Streamlit code editor widget loses user-pasted code content whenever a secondary UI tab is clicked. | Sprint 1 | kumkum | User Interface | Tied the Monaco/text input states directly into persistent st.session_state keys across all dashboard views. | 2026-07-16 | closed | User inputs and review histories persist securely without wiping out on tab switches.
7 | kumkum | 2026-07-16 | Uvicorn backend server crashes when processing a source file containing non-UTF-8 character encodings. | Sprint 1 | kumkum | Logical | Added explicit file encoding detection and fallback handling (errors="ignore" / utf-8) inside the file upload route. | 2026-07-17 | Closed | Non-standard text encodings are safely handled, preventing unexpected server shutdowns.
8 | kumkum | 2026-07-17 | Generated security vulnerability reports fail to export properly into downloadable markdown files | Sprint 1 | kumkum | User Interface | Configured Streamlit's st.download_button component with correct MIME types and byte-string data formatting. | 2026-07-18 | closed | Users can now successfully download generated analysis and remediation reports locally.
9 | kumkum | 2026-07-18 | Hardcoded Gemini API configuration secrets exposed in application logs during debug mode tracing. | Sprint 1 | kumkum | Standards | Scrubbed sensitive API key variables from print statements and implemented structured environment masking. | 2026-07-19 | Closed | Credentials are fully secured and protected from leaking into standard application logs.
10 | kumkum | 2026-07-19 | End-to-end multi-agent processing timeline exceeds standard timeout boundaries on larger codebases. | Sprint 1 | kumkum | Standards | Optimized asynchronous task execution handlers in FastAPI to process agent tasks concurrently where applicable.7/24/2026ClosedOverall execution time significantly reduced, ensuring a smooth and responsive user experience. | 2026-07-20 | closed | Overall execution time significantly reduced, ensuring a smooth and responsive user experience.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others